ACTION ITEMS

I - Sorted by Deadline, then by Responsible

(Actions with no explicit deadline considered due at the next Meeting 
for sorting purposes; this is not necessarily true in practice!)

| No. | Due | Responsible | Description |
| --- | --- | --- | --- |
| 06/04 | 2000/11 | Chairs | Outgoing and Incoming Chairs to respond to POGO regarding IGOS participation in POGO’s upcoming (Nov. 29) São Paulo meeting. |
| 06/02 | 2000/11/30 | Partners | Partners not directly participating in the IGOS Secretariat to identify their points-of-contact to the incoming IGOS-P Chairman by November 30, 2000, providing names and full addresses (including e-mail addresses for inclusion in the IGOS list server). |
| 06/08 | 2000/12/11 | Task team | Will Steffen, Jeff Tschirley, Alan Thomas and Colin Summerhayes to proceed with the development of an Integrated Global Carbon Theme in accordance with the IGOS Process guidelines. A revised draft proposal will be provided to the Secretariat for circulation among Partners by December 11, 2000, taking into account the comments made at IGOS-P 6. |
| 06/06 | 2001/01/10 | Partners | Partners to provide any comments on the TCO Theme report to Josef Cihlar by January 10, 2001. |
| 06/12 | 2001/01/10 | Partners | Partners to identify to Rick Lawford, as appropriate, attendees for the Water Cycle theme meeting of 8-10 January 2001 in Irvine, California, by December 1st, 2000. |
| 06/15 | 2001/01/10 | Task team | A small drafting group focused on the promotion of IGOS visibility to be set up under the lead of the IGOS-P Chair. As the initial task this group is to contribute by January 10, 2001, for consideration at CSD-9 in April 2001, a short explanatory paper on IGOS and draft texts for decision support on “Atmosphere” and “Information for Decision-Making”. The E.C., EUMETSAT, FAO, GCOS, NASDA, NOAA and UNEP offered voluntary participation in the drafting group. |
| 06/09 | 2001/01/15 2001/02/15 2001/03/15 | Partners Will Steffen Secretariat | Partners to provide Will Steffen with any comments on the IGCO revised draft proposal (Action 6/7) by January 15, 2001. A final draft should be provided by Will Steffen to the Secretariat by February 15. Partners’ consensus will be sought by March 15. |
| 06/07 | 2001/02 2001/03 | Josef Cihlar Secretariat | Josef Cihlar to incorporate Partners’ comments (Action 6/6) and ensure that a revised TCO report is consistent with the IGOS Process guidelines as soon as feasible after January 10, 2001. Partners’ consensus will be sought by early March. |
| 05/16 | 2001/03 | Partners | IGOS Partners encouraged to participate in the preparatory process for the April 2001 Commission on Sustainable Development 9th Session, advising UNEP and UNDESA of specific IGOS-related accomplishments or messages they would like to see reflected. |
| 05/17 | 2001/03 | UNEP and others | UNEP and interested parties, with support from the IGOS-P Chair/Liaison Group, to investigate the possibility of a dedicated IGOS side presentation at the April 2001 CSD. |
| 06/03 | 2001/03/15 | Task team | John Townshend, Colin Summerhayes, Peter Churchill (at the request of CEOS) and Don Hinsman (coordinating within WMO) to jointly produce and provide the Secretariat by March 15, 2001, with an appropriate set of IGOS DISS (Data and Information Systems and Services) recommendations to serve as Annex B of the revised Partners Process Paper. |
| 06/10 | 2001/04/02 2001/04/17 | IGCO Theme Team Secretariat | IGCO Theme Team to provide a draft, aimed at public release, of their proposed prospectus on the IGCO Process to the Secretariat by April 2, 2001, for review by the Partners by April 17. |
| 06/11 | 2001/05 | WCRP and task team | WCRP to lead a small group to develop a draft proposal by May 2001 for a Water Cycle theme. This will be reviewed at IGOS-P7 and approval will be sought at P8. Additional members in the small group include FAO, GCOS, IGBP and UNESCO. |
| 06/16 | 2001/06/01 | Chairs | Incoming IGOS-P Chair, in coordination with the incoming CEOS Chair, to prepare a letter seeking UN ACC support for IGOS-P initiatives, addressed to the UNESCO Director and other ACC Directors to whom Partner agencies are connected. |
| 06/05 | 2001/06/01 | GOOS | The Ocean Theme Implementation Team leader (GOOS) to invite appropriate POGO participation in the Team. |
| 06/14 | 2001/06/01 | IGACO team | Proponents of the IGACO concept to complete the development of a draft proposal to be presented to IGOS-P7, consulting as appropriate with TCO and IGCO to avoid duplication of efforts already underway. |
| 05/03 | 2001/06/01 | Partners | Partners urged to accept Ocean Theme Report as the strategy document for the implementation process and, as appropriate, to seek governing body approval at the earliest opportunity. [Just the part concerning governing body approval.] |
| 06/01 | 2001/06/01 | Partners | Partners are urged to contribute as possible in efforts to promote IGOS by organizing and committing resources to IGOS Special Sessions and exhibits in connection with international environmental Conventions and other related intergovernmental processes. |
| 05/18 | 2001/06/01 | Partners, IGOS-P Secr. and Theme Teams | Partners, the IGOS-P Chair/Liaison Group, and Theme Teams to provide IGOS documents of general interest to UNEP/Dahl for posting on the IGOS web site. [A standing action.] |
| 06/13 | 2001/06/01 | Secretariat | Secretariat to gather inputs and maintain a calendar of relevant meetings and publish it at the IGOS-P Website. |
| 06/17 | 2001/06/01 | Secretariat | Secretariat to identify gaps in the existing documentation available at the IGOS-P Website, obtain electronic versions and provide them to Arthur Dahl before the next IGOS-P meeting for inclusion. [This complements Action 5/18] |
| 05/15 | 2001/06/01 | UNEP and others | UNEP and other involved parties to continue the IGOS dialogue initiated in October 1999 with Scientific and Technical Subsidiary Bodies of International Environmental Conventions, reporting the results of such dialogue to Partners. [A standing action.] |

ACTION ITEMS

II - Sorted by Responsible, then by Deadline

(Actions with no explicit deadline considered due at the next Meeting 
for sorting purposes; this is not necessarily true in practice!)

| No. | Due | Responsible | Description |
| --- | --- | --- | --- |
| 06/04 | 2000/11 | Chairs | Outgoing and Incoming Chairs to respond to POGO regarding IGOS participation in POGO’s upcoming (Nov. 29) São Paulo meeting. |
| 06/16 | 2001/06/01 | Chairs | Incoming IGOS-P Chair, in coordination with the incoming CEOS Chair, to prepare a letter seeking UN ACC support for IGOS-P initiatives, addressed to the UNESCO Director and other ACC Directors to whom Partner agencies are connected. |
| 06/05 | 2001/06/01 | GOOS | The Ocean Theme Implementation Team leader (GOOS) to invite appropriate POGO participation in the Team. |
| 06/14 | 2001/06/01 | IGACO team | Proponents of the IGACO concept to complete the development of a draft proposal to be presented to IGOS-P7, consulting as appropriate with TCO and IGCO to avoid duplication of efforts already underway. |
| 06/10 | 2001/04/02 2001/04/17 | IGCO Theme Team Secretariat | IGCO Theme Team to provide a draft, aimed at public release, of their proposed prospectus on the IGCO Process to the Secretariat by April 2, 2001, for review by the Partners by April 17. |
| 06/07 | 2001/02 2001/03 | Josef Cihlar Secretariat | Josef Cihlar to incorporate Partners’ comments (Action 6/6) and ensure that a revised TCO report is consistent with the IGOS Process guidelines as soon as feasible after January 10, 2001. Partners’ consensus will be sought by early March. |
| 06/02 | 2000/11/30 | Partners | Partners not directly participating in the IGOS Secretariat to identify their points-of-contact to the incoming IGOS-P Chairman by November 30, 2000, providing names and full addresses (including e-mail addresses for inclusion in the IGOS list server). |
| 06/06 | 2001/01/10 | Partners | Partners to provide any comments on the TCO Theme report to Josef Cihlar by January 10, 2001. |
| 06/12 | 2001/01/10 | Partners | Partners to identify to Rick Lawford, as appropriate, attendees for the Water Cycle theme meeting of 8-10 January 2001 in Irvine, California, by December 1st, 2000. |
| 06/09 | 2001/01/15 2001/02/15 2001/03/15 | Partners Will Steffen Secretariat | Partners to provide Will Steffen with any comments on the IGCO revised draft proposal (Action 6/7) by January 15, 2001. A final draft should be provided by Will Steffen to the Secretariat by February 15. Partners’ consensus will be sought by March 15. |
| 05/16 | 2001/03 | Partners | IGOS Partners encouraged to participate in the preparatory process for the April 2001 Commission on Sustainable Development 9th Session, advising UNEP and UNDESA of specific IGOS-related accomplishments or messages they would like to see reflected. |
| 05/03 | 2001/06/01 | Partners | Partners urged to accept Ocean Theme Report as the strategy document for the implementation process and, as appropriate, to seek governing body approval at the earliest opportunity. [Just the part concerning governing body approval.] |
| 06/01 | 2001/06/01 | Partners | Partners are urged to contribute as possible in efforts to promote IGOS by organizing and committing resources to IGOS Special Sessions and exhibits in connection with international environmental Conventions and other related intergovernmental processes. |
| 05/18 | 2001/06/01 | Partners, IGOS-P Secr and Theme Teams | Partners, the IGOS-P Chair/Liaison Group, and Theme Teams to provide IGOS documents of general interest to UNEP/Dahl for posting on the IGOS web site. [A standing action.] |
| 06/13 | 2001/06/01 | Secretariat | Secretariat to gather inputs and maintain a calendar of relevant meetings and publish it at the IGOS-P Website. |
| 06/17 | 2001/06/01 | Secretariat | Secretariat to identify gaps in the existing documentation available at the IGOS-P Website, obtain electronic versions and provide them to Arthur Dahl before the next IGOS-P meeting for inclusion. [This complements Action 5/18] |
| 06/08 | 2000/12/11 | Task team | Will Steffen, Jeff Tschirley, Alan Thomas and Colin Summerhayes to proceed with the development of an Integrated Global Carbon Theme in accordance with the IGOS Process guidelines. A revised draft proposal will be provided to the Secretariat for circulation among Partners by December 11, 2000, taking into account the comments made at IGOS-P 6. |
| 06/15 | 2001/01/10 | Task team | A small drafting group focused on the promotion of IGOS visibility to be set up under the lead of the IGOS-P Chair. As the initial task this group is to contribute by January 10, 2001, for consideration at CSD-9 in April 2001, a short explanatory paper on IGOS and draft texts for decision support on “Atmosphere” and “Information for Decision-Making”. The E.C., EUMETSAT, FAO, GCOS, NASDA, NOAA and UNEP offered voluntary participation in the drafting group. |
| 06/03 | 2001/03/15 | Task team | John Townshend, Colin Summerhayes, Peter Churchill (at the request of CEOS) and Don Hinsman (coordinating within WMO) to jointly produce and provide the Secretariat by March 15, 2001, with an appropriate set of IGOS DISS (Data and Information Systems and Services) recommendations to serve as Annex B of the revised Partners Process Paper. |
| 05/17 | 2001/03 | UNEP and others | UNEP and interested parties, with support from the IGOS-P Chair/Liaison Group, to investigate the possibility of a dedicated IGOS side presentation at the April 2001 CSD. |
| 05/15 | 2001/06/01 | UNEP and others | UNEP and other involved parties to continue the IGOS dialogue initiated in October 1999 with Scientific and Technical Subsidiary Bodies of International Environmental Conventions, reporting the results of such dialogue to Partners. [A standing action.] |
| 06/11 | 2001/05 | WCRP and task team | WCRP to lead a small group to develop a draft proposal by May 2001 for a Water Cycle theme. This will be reviewed at IGOS-P7 and approval will be sought at P8. Additional members in the small group include FAO, GCOS, IGBP and UNESCO. |